## Construction Lien Comparison
Province | Statute | Lien Preserve Deadline | Lien Clock Triggers | Lien Perfect / Enforce Deadline | Statutory Holdback | Prompt Payment & Adjudication | Invoice → Payment Chain Timeline | Notices That Stop Clock / Shift Obligation
Alberta | Prompt Payment and Construction Lien Act (PPCLA) | 60 days (general); 90 days (oil & gas, concrete) | Completion or abandonment (fact dependent) | Action + CPL within ~180 days of registration | 10% holdback; release tied to lien period | Yes | Owner→GC: 28 days; GC→Sub: 7 days after payment; Sub→Sub‑sub: 7 days | Notice of non‑payment (owner within 14 days; GC within 7 days); notice of dispute
British Columbia | Builders Lien Act | 45 days | Completion, abandonment, termination, or certificate | Action and CPL required (timing fact dependent) | 10% holdback; 55‑day holdback period | No (Bill 20 passed, not in force) | N/A – no statutory prompt‑payment chain yet | N/A (until prompt payment in force)
Saskatchewan | The Builders’ Lien Act | 40 clear days | CSP, completion, or abandonment depending on chain | Action‑based enforcement (strict timelines) | 10% holdback concept | Yes | Owner→GC: 28 days; GC→Sub: 7 days after payment; Sub→Sub‑sub: 7 days | Notice of non‑payment within 14 days; notice to adjudicate
Manitoba | Builders’ Liens Act (with Prompt Payment reforms) | 60 days | Substantial performance, abandonment, or last supply | Action‑based enforcement (separate timing) | 7.5% holdback | Yes | Owner→GC: 28 days; GC→Sub: 7 days after payment; downstream same | Notice of non‑payment within statutory period; adjudication notice
Ontario | Construction Act | 60 days to preserve | CSP publication, completion, termination, or abandonment | 90 days to perfect after last preservation day | 10% holdback | Yes | Owner→GC: 28 days (14‑day notice window); downstream: 7 days after payment | Notice of non‑payment (owner 14 days; contractor 7 days); notice to adjudicate